## Data Processing Timeplan (hidden)
Phase | Task Name | Description | Duration | Rresource required | Deliverables
Design | Conceptual design | Design process model - with supporting diagrams - exhibiting the relations /functionalities /user roles | 10 days | Incountry support | defined and finalised field procedures and work flow
| Questionnaire structuring | Segment the sections at HH , IND level, roaster
| Task allocation | Each project member assigned tasks
| Adopting NHIES system | Structure a plan to amend/change existing NHIES applications
| Configure GIT server | Create users, roles
|  | Listing module ( design, code & test) | 20 days | 50 /50 inhouse
Develop | Pre-implementation |  | 20 days |  | working data entry application
| Data entry app | create dictionary |  | 50 /50 inhouse
create menu programs
Create forms and CAPI text
Develop the logic <>edit rules> and skip checks
|  | testing - Functionalities<DP & SM > | 20 days |  | signed off entry application + listing app
testing - usability <enumerators>
QA
| Synchronization app | configure data transmission script | 10 days | 50/50 | data transmission process setup
Do test with the server and peer -to- peer
| KMl files | test kml files with GIS team
| Training manuals | Design and compile training manuals, test case
| Post implementation | Develop & modify all programs | 20 days | incountry 50/50
| Edit Production runner | Modify the programs and the application
Do testing ( functionality, usability & stress test)
Documentation
Data collection |  | Support and training
Post data processing |  | Data Processing activities

## Census - summary
Phase | Task Name | Outcome | Milestones | Year to Census
Planning | Conceptual design | Project Data Management plan | Aprl -17/ 18 | Census -4Year
Design | Draft - design Census data management plan | Census systems specifications and procedures | April 18/19 | Census -3Year
Develop | Pre-implementation | Working system prototype | April 19/20 | Census -2Year
Testing | Functional nd Non functional system testing | Signed off Census Systems | April 19/20 | Census -2Year
Data collection | Updates and quality control | Data collection | April 19/20 | Census
Post data processing | Census dataset Version 1 | Census database version 1 | April 20/21 | Post Census

## Census - Detailed
Phase | Task Name | Outcome | Milestones | Year to Census
Planning | Conceptual design | Project Data Management plan | Aprl -17/ 18 | Census -4Year
Develop plan for data processing
Design the system architecture
Establish system requirements and resources
Design | Draft - design Census data management plan | Census systems specifications and procedures | April 18/19 | Census -3Year
Test the planned designed architecture
Final - design Census data management plan
Census System specification and requirements
Develop | Pre-implementation | Working system prototype | April 19/20 | Census -3Year
Develop the Menu Module
Develop data entry (CSEntry) Module
Develop post production Module
Develop filed quality assurance Module
Develop field reporting Module for web server
Testing | Functional and Non-functional system testing | Signed off Census Systems | April 19/20 | Census -2Year
Test web server configuration
Field test - data transmission
Real time reporting
Data collection | Updates and quality control | Data collection | April 19/20 | Census
Post data processing | Census dataset Version 1 | Census database version 1 | April 20/21 | Post Census
Data completeness and structure Module
Data recoding and editing Module
Data anonymization and transfer Module
| Secondary data editing and imputation | Census database version 2
Training and recruitment plan
Phase | Task Name | Outcome | Milestones | Year to Census | Costs (ea)
Recruitment | Recruit identified crucial positions | Critical positions filled | April 19/20 | Census -2Year
|  | Programmers x 2 | April 18/19 | Census -3Year
|  | Senior Programmers and Database administrator | April 18/19 | Census -3Year
|  | Programmers x 4 | April 19/20 | Census -3Year
Training | Training of programmers in CSWeb | Training report covering all the crucial process of CSWeb | April 18/19 | Census -3Year

## Sheet2
| Item | Quantity
1 | car charger | 1912
2 | internet modems | 1912
3 | projectors | 302
4 | Multifunctional printers around the country. | 76
5 | Tablets | 11430
6 | Screen protectors | 11430
7 | Power banks | 11430
8 | Tablets covers | 11430
9 | Car chargers | 2048
10 | Multifunctional printers | 15
11 | multi-plugs (5 plugs in each class * 302 classes) | 1510
12 | Network boosters | 150
13 | laptops with chargers | 50
14 | Network repeaters for the all the centres | 150
15 | Clome cast | 302